## NCCD CONTRACT NO. 1723-02

**NEW CASTLE CONSERVATION DISTRICT**

## Marshallton-Washington Avenue

**INVITATION FOR BIDS**

**BID PACKAGE**

**AND**

**SPECIFICATIONS**

##### COMPLETION: 30 WORKING DAYS

The attached copies of "Proposal and Schedule of Prices" in this booklet must be submitted and turned in for Bidding.

**MANDATORY PRE-BID 10:00 AM ON AUGUST 25, 2020**

**BIDS DUE BY 10:00 AM ON SEPTEMBER 3, 2020**

**NEW CASTLE CONSERVATION DISTRICT**

**NOTICE AND**

**INVITATION TO BID**

The New Castle Conservation District is inviting Bids for Contract No. 1723-02 Marshallton-Washington Avenuewhich includes the installation of RCP pipe, catch basins, drainage channel, roadway patching, and restoration.

The new construction is located in Marshallton, New Castle County, Delaware.

Bids will be received until 10:00 AM, September 3, 2020 in the New Castle Conservation District office, 2430 Old County Road, Newark, Delaware 19702, when they will be opened. Due to COVID-19 bids will not be read publicly. Specifications and instructions to bidders may be obtained from Ms. Liz Hook (302-832-3100 ext. 8970) at this office or from the website (http://www.newcastlecd.org/advertisedbid) on Monday August 17, 2020.  The office is located at the intersection of Business Route 896 and Old County Road. Please call to schedule an appointment if you are purchasing a set of plans and bid specs.

The District may extend the date and time for the opening of bids from that described herein with not less than five calendar days’ notice, by certified mail, to those prospective bidders who obtained copies of the bidding documents.

Plans and specifications obtained from the District office will cost $80 per set. (non-refundable) with check may payable to New Castle Conservation District.

There will be a mandatory pre-bid meeting on Monday, August 25, 2020 at 10:00 AM at the site to answer any questions regarding the project.

The completion time shall be 30 Working Days.

The terms of the contract shall require a bid security equivalent to 10% of the total bid amount and a performance & payment bond. A 5% Retainage is required upon payment(s) to be held for six months following completion of the contract.

New Castle Conservation District prohibits discrimination in its programs on the basis of race, color, national origin, sex, religion, age, disability, political belief and marital or family status.

 Dan Severson

 Acting Secretary

**INSTRUCTIONS TO BIDDERS**

The scope of this contract is as described on New Castle Conservation District plans entitled

 “Washington Avenue Drainage Improvements, signed and sealed on August 14, 2020" and these General and Special Provisions.

Specifications and additional information may be obtained at the District office at 2430 Old County Road (302-832-3100 ext. 8970 or from the website www.newcastlecd.org/advertisedbid.

Bids shall be made by completing and submitting the **"Proposal and Schedule of Prices"** **and the "Bid Security"** portions of this booklet.

Bid envelope shall carry a clear notation in the lower left quadrant,

"Bid for Marshallton-Washington Avenue- NCCD Contract No.1723-02**".**

Award, if any, will be made to the lowest and most responsive bidder. The District reserves the right to reject all bids and to waive minor irregularities and to refuse award to any bidder who has not satisfactorily completed work on a previous District project. Successful bidder shall be licensed and authorized to do business in the State of Delaware.

Bid Security: **REQUIRED**– 10% of bid amount

Performance & Payment Bond: **REQUIRED** – 100% of contract amount

Retainage: **REQUIRED** - 5% of contract payments

Mailing Address: New Castle Conservation District

 2430 Old County Road

 Newark, Delaware 19702

**STANDARD SPECIFICATIONS**

Unless otherwise specified in these contract documents and Special Provisions, DelDOT Standard Specifications, August 2001, with any and all Supplemental Specifications and addenda shall apply, and are hereby made part of this contract as fully and with the same effect as if attached or set forth at length herein.

Certain clauses in these Special Provisions represent modifications to the corresponding subsections of the Standard Specifications. In the case of conflicting requirements, these modifications shall govern, as specified in Subsection 105.06 of the Standard Specifications. Any applicable provision in the Standard Specifications not amended by and not in conflict with any Special Provisions shall be understood to be in full effect.

DelDOT Standard Drawings shall govern the details required for the construction of curbs, gutters, sidewalks, drainage inlets, manholes, junction boxes, etc. unless otherwise required in these specifications. Details of DelDOT's Standard Specifications and/or Standard Drawings are available on the DelDOT website – <http://www.deldot.gov/information/pubs_forms/manuals/standard_specifications/index.shtml> and http://www.deldot.gov/information/pubs\_forms/const\_details/index.shtml.

**GENERAL PROVISIONS**

All bids shall be accompanied by a deposit of either a good and sufficient bond to the State of Delaware for the benefit of the District, with corporate surety authorized to do business in the State of Delaware, with warrant of attorney to confess judgment, or a certified check drawn on a responsible banking institute, paying to the order of the New Castle Conservation District for Ten (10) percent of the total amount of the bid which deposit is to be forfeited as liquidated damages in case the bid is accepted and the bidder shall fail to execute a contract within twenty (20) calendar days after notification of award.

The deposit shall be returned to the successful bidder upon execution of the contract and the deposits of unsuccessful bidders shall be returned to them immediately upon the awarding of the contract.

Upon award of the contract, the contractor shall execute the contract and provide a performance and payment bond within 20 calendar days after contract award.

All contract work shall be completed within **30 Working Days** and time charges shall commence as specified in the "Notice to Proceed" letter. Section 101.91 "Working Day" of DelDOT Specifications is revised as follows: Item 4 in the first sentence is deleted. Work days shall be charged between December 16 and March 15 when the weather is deemed suitable by the District for prosecution of the work on the contract.

The District will issue to the Contractor a Notice to Proceed which will stipulate the date on or before which the Contractor is expected to begin work. The date specified in the Notice to Proceed will be at least ten calendar days subsequent to the date of issuance of the Notice to Proceed. No work is to be started before receipt of the Notice to Proceed. The specified contract time shall begin on the day the work actually starts or on the date stipulated in the Notice to Proceed, whichever is earlier.

In the event the contractor fails to complete the project in the contract specified period, default shall be announced.  At that time, the District shall offer to let the contractor continue under the specific liquidated damage assessment of **$1,030 per Working Day**.  If the Contractor rejects the offer, the District reserves the right to terminate the contract. Compensation for work completed and materials provided to the job will be calculated by the District.  After a deduction for necessary administrative costs associated with terminating the contract, payment will be made to the Contractor of the remaining funds.

**CONTRACT INSPECTION**

An inspector representing the New Castle Conservation District will be present on the project.

**NON-DISCRIMINATION**

New Castle Conservation District prohibits discrimination in its programs on the basis of race, color, national origin, sex, religion, age, disability, political belief and marital or family status. Contractors and subcontractors working on NCCD contracts shall comply with these requirements.

**HOLIDAYS**

All Saturdays, Sundays, and Holidays as listed below are non-work days for the District. The District will consider allowing the contractor to work on Saturdays, Sundays, and Holidays providing a written request is received at the District office at least 3 calendar days prior to the event and the Contractor agrees to reimburse the District at 1.5 times the inspector's hourly billing rate for Saturdays and 2.0 times for Sundays or Holidays up to eight (8) hours.  No more than eight (8) hours shall be worked. No work is to be performed without approval of the District. If the Contractor receives permission and works on a Sunday or holiday, full working days will be charged, weather permitting. No time will be charged for work on Saturdays.

**\*\*\*Official District Holidays for Calendar 2020**\*\*\*

 January 1, 2020 New Year’s Day Holiday

 January 20, 2020 Martin Luther King Jr. Day

 February 17, 2020 President's Day

 May 25, 2020 Memorial Day

 July 3, 2020 Independence Day

 September 7, 2020 Labor Day

 October 12, 2020 Columbus Day

 November 11, 2020 Veterans Day

 November 26, 2020 Thanksgiving Day

 November 27, 2020 Thanksgiving Friday

 December 25, 2020 Christmas Day

**WORK SCHEDULE**

A work schedule is required for this contract.

**INSURANCE**

The Contractor will maintain insurance coverage in amounts not less than the following: (a) Workers Compensation with Statutory Employer Liability Limits for the state or states in which the work is to be performed; (b) Comprehensive General Liability Insurance including Products and Completed Operations and Blanket Contractual Liability in the amount of $1,000,000 per occurrence / $2,000,000 General Aggregate / $2,000,000 Products and Completed Operations Aggregate / $1,000,000 Personal Injury and Advertising Liability / $50,000 Property Damage Liability / and $10,000 Medical Payments. In addition to the foregoing, contracts that involve Professional Liability (Errors and Omissions) the contractor will be required to maintain at least a Limit of Liability of $500,000 per Claim with at least $500,000 Policy Aggregate. The Contractor will maintain all coverage in force for the duration of the contract and have issued a Certificate of Insurance to the **District**. In the event of cancellation of any insurance coverage the **District** requires a 30 day notice prior to cancellation. The Contractor shall hold the **District** and its agents harmless from claims resulting from events pertaining to this contract such as, but not limited to, trespass, property damage, personal injury, poor workmanship, inferior materials, liens of suppliers and subcontractors, and theft.

**UTILITIES**

**Delete Subsection 105.09 and replace with the following:**

It shall be the Contractor’s responsibility to accurately locate all existing utilities such as gas, sewer, electric, water, telephone, etc. The Contractor shall take every precaution to prevent damage to any utility facilities. The Contractor shall be financially responsible for the repair of any utilities damaged as a result of his construction activities. The following shall be contacted for assistance in identifying the locations of utilities prior to commencing any activities on the project.

MISS UTILITY 1-800-282-8555

New Castle County Sewer 395-5700

City of Wilmington 576-3060

The Contractor shall contact the appropriate utility companies at least ten days prior to construction when adjustment or relocation is necessary. Upon approval of the estimate by the District, the Contractor shall submit invoices for the relocation work to the District for payment. These costs shall not be included in any bid prices for the contract.

**PERMITS AND EASEMENTS**

The District shall obtain any permits required from DelDOT for work within State Rights-of-Way.

Construction Easements have been granted by affected property owners and are available upon request to the District office.

The Contractor shall be responsible for any permits, ingress/egress and construction rights-of-way not provided by the District, including any required DelDOT Temporary Construction Entrance permit.

**PROPERTY MARKERS**

The Contractor shall be responsible to protect any identified or found property markers or monuments and shall replace, at the Contractor's own expense, any markers or monuments disturbed during construction using a Delaware Professional Land Surveyor (PLS) or Delaware Professional Engineer (PE). The PLS or PE shall provide a letter certifying and describing the work done in resetting any markers or monuments.

**REGULATIONS**

The Contractor and all Subcontractors shall comply with all applicable Federal, State, County and Municipal laws, rules and regulations during the construction of this project, including but not limited to the following:

 Construction Occupational Safety and Health

 Equal Employment Opportunity

 Sediment and Storm Water Management

**These contract documents do not include the necessary components for construction safety. It is the overriding intention of the parties of this contract that nothing in this paragraph requires the District, its employees or its agents to be responsible for any aspect of safety during construction of this contract or to ensure that the Contractor follows whatever safety regulations which may be applicable.**

**THIRD PARTY AGREEMENTS**

The Contractor shall obtain the District's consent prior to making any third party agreements with regard to this contract.

**SUBCONTRACTORS**

All proposed Subcontractors shall be approved in writing by the District prior to any work being done by same. The Contractor shall perform a minimum of 50% of the work on the contract with his own forces.

**EXAMINATION OF SITE, PLANS AND SPECIFICATIONS:**

The bidder shall examine carefully the site of the proposed work, the proposal, plans and specifications and contract forms before submitting a proposal. The submittal of a bid shall be prima facie evidence that the bidder has made such examinations and is satisfied as to the conditions to be encountered in performing the work and as to the requirements of the plans, specifications and contract. No additional payments shall be made for the completion of this contract, other than payment for the bid items included herein except as provided in these specifications.

**CHANGE IN SCOPE OF WORK**

The District reserves the right to change the scope of work through alteration, addition or deletion.  If such changes involve other than increasing or decreasing contract bid quantities, the District will initiate cost negotiations for the extra work. The District Chairman shall reserve the right to issue unilateral work directives and payment when agreement cannot be reached.

**CHANGE OF CONTRACT BID QUANTITIES**

The District reserves the right to increase or decrease contract quantities at the contract unit bid prices. Any such changes in contract quantities shall not be grounds for changes in the unit bid prices.

**INSPECTIONS**

A semi-final inspection will be held at the request of the Contractor, at completion of the project. Any deficiencies will be noted at that time. Any requests for additional compensation shall be made at that time by the Contractor. Payment, less **5%** retainage, will be made within 30 days of the semi-final acceptance of all work. An inspection will be held at six months’ time following semi-final or conditional acceptance, and final payment will be made if all work is found satisfactory and all required reports, drawings, etc. turned in and accepted.

**PAYMENTS**

The New Castle Conservation District will make a lump sum payment every 30 calendar days as the Contractor submits estimates for work completed on the bid schedule and as determined and approved by the Engineer. In making such progress payments, there shall be retained **5%** of the estimated amount until final inspection and acceptance of the contract work. The retainage of 5% shall be held by the District for six months after the semi-final inspection and may be used to make repairs to any defects in materials or workmanship which may become evident during this time period in the event that the Contractor does not make such repairs at his expense. A final inspection will be conducted approximately six months after the semi-final inspection, at which time the final acceptability of the project will be determined. Retainage will be returned to the Contractor when all work, including reports, drawings, etc., is found acceptable.

**DEFINITIONS**

Contracting Officer District official, or designee authorized to enter into all money obligating contracts.

Program Manager Administers the District Construction Program. May make recommendations for changes in contract quantities, extra work items. Can direct field changes or approve recommendations for field changes and hear contractor claims. Coordinates Project Engineer, Planner and Inspector activities.

DelDOT The Delaware Department of Transportation

DelDOT The Delaware Department of Transportation’s

Specifications Standard Specifications for Road and Bridge Construction dated August 2001 with any addenda or Supplemental Specifications issued.

Disposal Off Site Disposal off site requires that materials will be disposed of at an approved facility or an operating landfill. The contractor must notify the District as to the location of the disposal site. If other than a previously approved facility or operating landfill will be used, the contractor is responsible to obtain all permits, approvals, investigations, etc. required to use such site and must provide documentation of same to the District.

District The New Castle Conservation District

Fixed Price Item A fixed price item is defined as an item where the District establishes the price of the item in the contract bidding documents. The Contractor, by virtue of bidding the contract, agrees to do the work at the price stated in the bidding documents for the actual number of bid units which are completed and accepted.

Fixed Quantity Item A fixed quantity item is defined as an item where the District determines the fixed quantity in the bidding documents, which will be used as measurement for payment of the item of work, realizing that the actual quantity of work performed on the project may vary somewhat either above or below the established fixed quantity. By virtue of the Contractor bidding the contract, he shall agree to do the work at the contract unit price bid for the exact quantity stated in the bidding documents. The exact quantity established in the bidding documents shall only be adjusted as provided in these specifications under "Basis of Payment For Fixed Quantity Items".

Inspector Individual representing District on site who ensures quantity and quality of work completed is in accordance with specifications. Reports to Program Manager.

Change Order Written order issued by Contracting Officer to the Contractor to change, add or delete work.

Planner Responsible for developing scope of project in conjunction with Engineer, landowners and District officials.

Project Engineer Responsible for design of project. Makes recommendations for field changes. May approve shop and/or working drawings.

NRCS Specifications Standard Specifications of the U.S. Department of Agriculture, Natural Resources Conservation Service.

Working Day A working day is defined as any calendar day exclusive of Saturdays, Sundays or District holidays when the Contractor can prosecute the work. The application and interpretation of work day charges will be in accordance with DelDOT Specifications except **work days shall be charged between December 16 and March 15 when the weather is deemed suitable by the DISTRICT for prosecution of the work on the contract.**

**BASIS OF PAYMENT FOR FIXED QUANTITY ITEMS**

When indicated on the plans, special provisions or bidding documents, certain items may be paid for on an estimated fixed quantity item basis. Such items will be specifically identified as **Estimated Fixed Quantity (EFQ)** items. Where this occurs, the method of measurement and basis of payment indicated in DelDOT Standard Specifications for such items are deleted.

When estimated fixed quantities are indicated, the only quantities for which payment will be made are the estimated quantities as shown in the proposal at the unit price bid.

The bidder should check the estimates and make his/her own appraisal of the amount of labor, equipment, and/or material required to complete the work in accordance with the plans and specifications. No allowance will be made or claims considered for any quantities used in completing the work in excess of those given in the proposal unless changes are authorized in writing by the Engineer.

In the case where the actual quantities differ from the fixed quantities indicated in the proposal by more than 25%, additions or deductions will be made to or from the proposed quantities for the actual volume or amounts in excess or deficient of the 25%, with payment adjusted in accordance with the unit bid price of the item. No claim shall be made by the Contractor for anticipated profits or for the costs of other items of work which he may have included in the item. The Contractor is cautioned not to include any other hidden contract costs or unbalanced bidding in the item.

**MINIMUM WAGE RATES**

The rates of wages contained herein shall be the minimum wage rates to be paid by the Contractor and any Subcontractor on the project when costs of this contract exceeds $500,000.00 for new construction (including painting and decorating) or $45,000.00 for alteration, repair, renovation, rehabilitation, demolition or reconstruction (including painting and decorating) of buildings or works.

A workday shall be considered eight hours and any employee of the Contractor or Subcontractor shall be paid time and one-half for any work done in excess of forty hours per week.

The Contractor shall forfeit as a penalty to the New Castle Conservation District the sum prescribed by Delaware Law for each laborer, workman or mechanic employed for each calendar day, or portion thereof, for when such laborer, workman or mechanic is paid less than the stipulated rates for any work done under the said contract, by him, or any Subcontractor under him.

New Castle Conservation District shall withhold and retain there from all sums and amounts which shall have been forfeited pursuant to these stipulations, provided however, that no sum shall be withheld or retained except from final payment without a full investigation by the District Coordinator.

Contractor may withhold from any of his Subcontractors sufficient sums to cover any penalties withheld by New Castle Conservation District due to the Subcontractor's failure to comply with the terms of this contract.

Nothing in this contract, however, shall be construed to prohibit the payment to any laborer, workman or mechanic employed on work in the scope of this contract of more than the stated wage rate.

In the event that any sum shall be withheld or forfeited under the terms set forth, it shall be the duty of the New Castle Conservation District to determine the amount due and owed to the laborers, mechanics and workers under the terms of this contract and make full restitution of same from the amount so withheld.

**The Delaware Code (Title 29, Chapter 69, Section 6960, Paragraph (c)) requires the contractor to furnish weekly sworn payroll information to the Department of Labor. The Department of Labor shall keep and maintain the sworn payroll information for a period of six months from the last day of the work week covered by the payroll.**

If the Contractor needs further clarification pertaining to prevailing wage rates, the District has on file two publications published by the Delaware Department of Labor, entitled "Delaware Prevailing Wage Regulations" and "Classification of Workers Under Delaware Prevailing Wage Law." These publications are available for review upon request.



**SPECIAL PROVISIONS**

**GENERAL DESCRIPTION OF PROJECT**

This project involves the installation of a closed drainage system in Marshallton. Work includes RCP

pipe, catch basins, hot mix patching, channel excavation, stabilization, and restoration of disturbed areas.

**EROSION AND SEDIMENT CONTROL**

The Contractor shall comply with all aspects of Delaware and/or New Castle County Erosion and Sediment Control requirements. The costs involved in meeting these requirements shall be included in the bid items in this contract. No separate payment shall be made for compliance with these regulations other than those individual erosion and sediment control related bid items that are specifically listed in this contract.

**ACCESS TO THE SITE**

Access to the site is from Washington Avenue and Old Capital Trail.

**CONSTRUCTION LIMITS**

The construction right-of-way or work area limits shall be established on the plans and/or described at the pre-bid meeting on site.

**CONSTRUCTION PLANS AND SPECIFICATIONS**

Eight (9) sheets entitled "New Castle Conservation District Contract No.1723-02" prepared by the New Castle Conservation District and signed and sealed on August 14, 2020, Standard Specifications and Special Provisions shall govern the construction of this project.

**ITEM #SP-3 TEST HOLES OR TEST PITS FOR UTILITY LOCATION**

**DESCRIPTION OF WORK -** When precise information is needed regarding the exact location of buried utilities or structures, the Contractor shall excavate test holes and test pits in accordance with Section 202 of DelDOT Standard Specifications.

**METHOD OF MEASUREMENT -** The quantity of Test Holes to be paid for will be at the actual number of test holes excavated, as shown on the plans and as directed, and accepted.

**BASIS OF PAYMENT -** The quantity of Test Holes, measured as provided above, will be paid for at the contract unit price bid per each for this item, which price and payment will constitute full compensation for excavating (using hand excavation when necessary), placing and compacting backfill, and for all labor, materials, equipment, tools, and incidentals required to complete work.

**ITEM #SP-4 CHANNEL EXCAVATION**

**DESCRIPTION OF WORK -** This work consists of widening and deepening existing stream channels and waterways, reconstructing channel and stream configurations and locations, shaping and finishing channel and stream beds and banks, and removing sediment and debris from stream channels. Work shall conform to lines and grades and typical sections shown on the drawings and no allowance shall be made for undercutting.

 The Contractor is responsible for the removal and disposal off-site of all excess excavation, spoil and debris. The contractor shall notify the District in writing as to the location of the disposal site. Should the contractor elect to dispose of excess materials at other than an operating landfill or previously approved disposal site, the contractor is responsible for obtaining all permits, investigations, approvals, etc. required to use such site and must provide documentation of same to the District.

**CONSTRUCTION METHODS -** Construction methods for Channel Excavation shall conform to section 203 of the DelDOT Specifications.

**METHOD OF MEASUREMENT -** The amount of Channel Excavation will not be measured; however, the work to be paid for shall be that specified and completed within the limits of the project, as shown on the drawings or the number of lineal feet of Channel Excavation to be paid for under this item shall be the actual number of linear feet of Channel Excavation in accordance with these specifications, measured from end to end along the alignment of the installation, complete, in place and accepted.

**METHOD OF PAYMENT -** Channel Excavation within the limits of construction shall be paid for at the lump sum price or unit bid price for the item “Channel Excavation,” which price and payment shall constitute full compensation for all labor, equipment, tools, and incidentals necessary to complete the work.

**ITEM #SP-11 HOT MIX PATCHING (REMOVAL AND REPLACEMENT)**

**DESCRIPTION OF WORK -** Hot Mix Patching shall include saw cutting existing pavement to provide for a patch, removing existing pavement and pavement base in the patch area and placing concrete pavement base and hot mix pavement.

**MATERIALS AND CONSTRUCTION METHODS -** Concrete for base shall meet DelDOT Specifications for Section 500 Class A concrete. Hot Mix Asphaltic Concrete shall meet DelDOT Specifications for Section 401Type C Hot Mix Asphaltic Concrete.

**METHOD OF MEASUREMENT -** The quantity of Hot Mix Patching to be paid under this item shall be the actual square yards as measured along the surface of the roadway patch, complete, in place, and accepted.

**BASIS OF PAYMENT -** The square yards of Hot Mix Patching as measured above shall be paid at the contract unit price bid for the item, which price shall include full compensation for saw cutting existing pavement, pavement removal, replacing pavement base with portland cement concrete, and placing hot mix asphaltic concrete surface course.

**ITEM #SP-14 PORTLAND CEMENT CONCRETE CURB AND INTEGRAL CURB & GUTTER**

**DESCRIPTION OF WORK -** The contractor shall install P.C.C. Curb and/or Integral P.C.C. Curb & Gutter as shown on the plans. This item shall include sawcutting existing curb, gutter and pavement, removal and disposal off-site of existing curb, gutter and pavement, excavation for curb and gutter, furnishing and placing graded aggregate base course (GABC) for curb and gutter and hot-mix patch, placing P.C.C. Curb and/or Integral P.C.C. Curb & Gutter, backfilling along installed curb and gutter, replacing topsoil over backfilled area, sealing joints and construction of a hot-mix patch on a GABC base between the new curb and gutter and the existing pavement.

**MATERIALS AND CONSTRUCTION METHODS -** The materials and construction methods for this item shall conform to DelDOT's Specifications for Sections 302, 406, and 701.

**METHOD OF MEASUREMENT -** The number of linear feet of P.C.C. Curb and/or Integral P.C.C. Curb & Gutter to be paid for under this section shall be the actual number of linear feet of P.C.C. Curb and/or Integral P.C.C. Curb & Gutter measured from end to end, complete, in place, and accepted. The costs of joints and joint sealer shall be included in the price bid per linear foot for this item.

**BASIS OF PAYMENT -** The number of linear feet of P.C.C. Curb and/or Integral P.C.C. Curb & Gutter measured as provided above, shall be paid for at the contract unit price per linear foot bid for this item, which price and payment shall be full compensation for sawcutting existing curb, gutter and pavement; removing and stockpiling existing topsoil; removing and disposing of existing curb, gutter and pavement off-site; excavation; furnishing, hauling, and installing graded aggregate base course and P.C.C. Curb and/or Integral P.C.C. Curb & Gutter; backfilling with excavation material; replacing stockpiled topsoil over the backfilled area; finish grading of the area to accommodate sod or seed and mulch; sealing joints; and constructing a hot mix patch between the new curb & gutter and the existing pavement. No separate payment will be made for the items herein listed under this item of work.

**ITEM #SP-14 PORTLAND CEMENT CONCRETE CURB AND INTEGRAL CURB & GUTTER**

**DESCRIPTION OF WORK -** The contractor shall install P.C.C. Curb and/or Integral P.C.C. Curb & Gutter as shown on the plans. This item shall include sawcutting existing curb, gutter and pavement, removal and disposal off-site of existing curb, gutter and pavement, excavation for curb and gutter, furnishing and placing graded aggregate base course (GABC) for curb and gutter and hot-mix patch, placing P.C.C. Curb and/or Integral P.C.C. Curb & Gutter, backfilling along installed curb and gutter, replacing topsoil over backfilled area, sealing joints and construction of a hot-mix patch on a GABC base between the new curb and gutter and the existing pavement.

**MATERIALS AND CONSTRUCTION METHODS -** The materials and construction methods for this item shall conform to DelDOT's Specifications for Sections 302, 406, and 701.

**METHOD OF MEASUREMENT -** The number of linear feet of P.C.C. Curb and/or Integral P.C.C. Curb & Gutter to be paid for under this section shall be the actual number of linear feet of P.C.C. Curb and/or Integral P.C.C. Curb & Gutter measured from end to end, complete, in place, and accepted. The costs of joints and joint sealer shall be included in the price bid per linear foot for this item.

**BASIS OF PAYMENT -** The number of linear feet of P.C.C. Curb and/or Integral P.C.C. Curb & Gutter measured as provided above, shall be paid for at the contract unit price per linear foot bid for this item, which price and payment shall be full compensation for sawcutting existing curb, gutter and pavement; removing and stockpiling existing topsoil; removing and disposing of existing curb, gutter and pavement off-site; excavation; furnishing, hauling, and installing graded aggregate base course and P.C.C. Curb and/or Integral P.C.C. Curb & Gutter; backfilling with excavation material; replacing stockpiled topsoil over the backfilled area; finish grading of the area to accommodate sod or seed and mulch; sealing joints; and constructing a hot mix patch between the new curb & gutter and the existing pavement. No separate payment will be made for the items herein listed under this item of work.

**ITEM #SP-15 RIPRAP**

**DESCRIPTION OF WORK -** This item shall consist of furnishing and placing riprap of the class required by the contract in accordance with these specifications and in reasonably close conformity with the lines, grades, dimensions and locations shown on the plans or established by the Engineer. This item shall also include excavation, furnishing and placing geotextile fabric when shown on plans, removal of unsuitable material, backfill, embankment and clearing and grubbing as may be required to complete the work as indicated on the plans, or as directed.

**MATERIALS -** Stone for riprap shall be sound, durable, and hard, free from lamination, weak cleavages and undesirable weathering. All stone shall be new, rough quarry stone approximately rectangular in cross section and free from thin slab pieces having a maximum dimension more than two and one-half times the least dimension. Geotextile fabric shall be as noted on plan or shall conform to DelDOT's Specifications for Section 827, Geotextile.

**GRADATIONS- LARGE RIPRAP (DELDOT SPECIFICATIONS)**

**Percent Passing (Square Openings) by Weight**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **NCSA\* Rock Size** | **Weight\*\*** | **R-7** | **R-6** | **R-5** | **R-4** |
| 30" |  ± 1800# | 100\*\*\* |   |   |   |
| 24" |  ± 900# |   | 100\*\*\* |   |   |
| 18" |  ± 400# | 15-50 |   | 100\*\*\* |   |
| 12" |  ± 100# |   | 15-50 |   | 100\*\*\* |
| 9" |  ± 50# | 0-15 |   | 15-50 |   |
| 6" |  ± 15# |   | 0-15 |   | 15-50 |
| 4" |  ± 5# |   |   | 0-15 |   |
| 3" |  ± 1.6# |   |   |   | 0-15 |

\* National Crushed Stone Association

\*\* Maximum Weight Stone – Estimated and Informational Only

\*\*\* Maximum Allowable Rock Size

**The contractor will provide certification from the supplier that the riprap furnished for the project meets the requirements of the specifications.**

**METHOD OF MEASUREMENT -** Stone for this section shall be measured by the ton as verified by certified weight slips showing the net weight for each load of stone delivered and incorporated into the project.

**BASIS OF PAYMENT -** The tonnage measured as provided above placed and accepted shall be paid for at the contract unit price per ton bid for riprap, which price and payment shall be full compensation for excavation, furnishing and placing riprap and geotextile fabric when shown on plans, removal and disposal of unsuitable material, backfill, embankment, clearing and grubbing and for all labor, equipment, tools and incidentals necessary to complete the item.

**ITEM #SP-19 SCREENED TOPSOIL**

**DESCRIPTION OF WORK** - This item shall consist of ground preparation, furnishing and placing screened topsoil for establishing vegetative cover when there is an insufficient quantity of topsoil salvaged from the job site to meet project requirements.

**MATERIALS AND CONSTRUCTION METHODS** - Topsoil shall be a loam, sandy loam, clay loam, silt loam sandy clay loam, loamy sand or other soil approved by the Engineer. It shall not have a mixture of contrasting textured subsoil and shall not contain slag, cinders, stones, lumps of soil, sticks, roots, trash or other extraneous material larger than 1/2" in diameter. . Immediately prior to dumping and spreading the topsoil, the subgrade shall be loosened by discing or by scarifying to a depth of at least 3 inches. Topsoil shall be uniformly distributed and compacted to a minimum of four inches to conform to the required final grades. Compaction shall be done with a minimum 18” diameter by 24 inch wide roller weighing a minimum of 225 pounds or an approved equivalent or by passing a bulldozer up and down slope to create horizontal erosion check slots. Spreading shall be performed in such a manner that seeding can proceed with a minimum of additional soil preparation and tillage

The materials and construction methods for topsoiling shall be according to Delaware Erosion & Sediment Control Handbook Detail No. DE-ESC-3.4.1.

**NOTE: Topsoil may be paid either by weight or lump sum. The bidder is instructed to refer to the “PROPOSAL AND SCHEDULE OF PRICES’ included in this bid package to determine which method applies to this contract.**

**METHOD OF MEASUREMENT** - When paid by weight, the quantity of topsoil to be paid will be the actual number of tons provided, as documented by certified weight slips, complete, in place, and accepted.

When paid lump sum, topsoil will not be measured; however, the work to be paid for shall be that required to complete the project, performed in accordance with the requirements of these specifications, complete, in place, and accepted.

**BASIS OF PAYMENT** - The quantity of Topsoil, measured as determined above as applicable to this contract, will be paid at the contract unit price bid for this item, which price and payment shall be full compensation for preparation of the grade, furnishing, hauling and placing all materials, and for all labor, equipment, tools and incidentals necessary to complete the work.

**ITEM #SP-28 CONSTRUCTION ENGINEERING**

**DESCRIPTION OF WORK -** This item shall consist of providing survey for layout and construction. The Contractor shall provide an experienced, competent engineering/surveying staff working under the direction of a Professional Engineer or Professional Land Surveyor licensed in the state of Delaware, to set the lines and grades necessary to construct the project. The Contractor shall perform all construction layout from the information provided on the drawings.

Construction engineering shall include establishing all control points, reference points, elevations, grade stakes, etc., as required for completion of the project. All computations necessary for completion of this item shall be made and preserved by the Contractor. All computations, survey notes and other records necessary to accomplish the work shall be made available to the District upon request.

The engineer may check all or any portion of the survey work or notes made by the Contractor and any necessary correction to the work shall be made immediately. Such checking shall not relieve the Contractor of his responsibility for the accuracy or completeness of the work. The Contractor shall assume full responsibility for any errors and/or omissions in the work of the engineering/surveying staff in the performance of this item.

AS-BUILT DRAWINGS - During the progress of the work, the Contractor shall keep a careful record at the job site of all changes and deviations from the layouts shown on the Contract Drawings. The Contractor shall record such changes and deviations on the prints of the Contract Drawings immediately. These drawings will be made available to NCCD for inspection or checking at any time during the construction period. At the time of Semi-Final Inspection of the work, the Contractor shall turn over to NCCD one (1) set of clean, white prints of the Contract Drawings with all the aforementioned as-built information neatly recorded thereon in red. The Contractor shall include on the As-Built Drawings an as-built survey of constructed conditions consisting of the following items:

1. Lines and grades of all disturbed areas.
2. Invert elevations of all structures (existing and constructed).
3. the actual location referenced from at least two (2) permanently fixed surface structures of all sub-surface utilities of work installed

**METHOD OF MEASUREMENT -** Construction engineering will not be measured.

**BASIS OF PAYMENT -** Construction engineering will be paid at the contract lump sum price bid for this item, which price and payment shall be full compensation for furnishing all labor, equipment, instruments, stakes and other material and incidentals necessary to complete the work. Monthly payment will be made under this item in proportion to the amount of work done as determined by the Engineer.

**ITEM #SP-29 SEEDING & SOIL STABILIZATION MATTING**

**DESCRIPTION OF WORK -** All disturbed areas shall be seeded and stabilized with matting as specified herein and as shown on the plans or as directed by the Engineer. This item shall consist of ground preparation, furnishing and placing seed, fertilizer, limestone and matting in accordance with these specifications, the manufacturer’s specifications, the notes, details on the plans, and/or as directed by the Engineer.

**MATERIALS -** Stabilization matting shall be of the Type specified on the plans or as directed by the Engineer. The seed mixtures shall be as shown on the Plans and in accordance with Delaware Erosion and Sediment Control Handbook Detail No. DE-ESC-3.4.3 unless directed otherwise by Engineer. The contractor shall submit seed mix certificates and matting for approval prior to seeding, and shall provide certified delivery slips of all seed, fertilizer, ground limestone and matting.

**Soil Stabilization Matting** Types I through IV (SSM-I through SSM-IV) are temporary to long-term degradable mattings, applied to the soil surface to prevent erosion prior to vegetative establishment. They can be used both in slope applications and as temporary channel liners. All materials shall be in accordance with Delaware Erosion and Sediment Control Handbook Detail No DE-ESC-3.4.6.1 unless directed otherwise by Engineer.

**SSM-I** is a temporary mat that will degrade within 12 months. It is composed of 100% agricultural straw (min 0.5 lbs/SY) or 100% wood excelsior fiber (min 0.8 lbs/SY, min 80% six-inch or longer fiber length) with a single top netting of biodegradable material. An **SSM-I** is acceptable on slopes of 3:1 or flatter and in low flow swales with a maximum design shear stress of 1.55 psf, where natural vegetation will provide permanent stabilization. Example Products: North American Green S75BN, East Coast Erosion Blankets ECS-1B.

**SSM-II** is also a temporary mat that will degrade within 12 months. It is also composed of 100% agricultural straw (min 0.5 lbs/SY) or 100% wood excelsior fiber (min 0.8 lbs/SY, min 80% six-inch or longer fiber length), but it contains a double netting (top and bottom) of biodegradable material. An **SSM-II** is acceptable on slopes of 2:1 or flatter and in low flow swales with a maximum design shear stress of 1.65 psf, where natural vegetation will provide permanent stabilization. Example Products: North American Green S150BN, East Coast Erosion Blankets ECS-2B.

**SSM-III** is an extended term mat lasting 12 to 24 months. It is composed of 70% agricultural straw or wood excelsior fiber and 30% coconut (coir) fibers with two woven biodegradable nettings. An **SSM-III** is acceptable on slopes of 1.5:1 or flatter and in medium flow swales with a maximum design shear stress of 1.80 psf, where natural vegetation will provide permanent stabilization. Example Products: North American Green SC150BN, North American Green C125BN, East Coast Erosion Blankets ECC-2B.

**SSM-IV** is a long term mat lasting 18 to 36 months. It is composed of 100% coconut (coir) fibers or 100% polypropylene fibers with two plastic or woven biodegradable nettings with UV stabilization. An **SSM-IV** is acceptable on slopes of 1:1 or flatter and in high flow swales with a maximum design shear stress of 2.0 psf, where natural vegetation will provide permanent stabilization. Example Products: North American Green C125, Synthetic Industries Landlok C2, East Coast Erosion Blankets ECC-2 Double Net Coconut.

**CONSTRUCTION METHODS -** The construction methods for seeding and soil stabilization matting shall be according to Delaware Erosion & Sediment Control Handbook Detail No. DE-ESC-3.4.3 and 3.4.6.1.

The area(s) to be seeded shall be topsoiled or disked or scarified to a depth of 4" to form a loose, friable layer of soil, free of clods, rocks and extraneous matter one inch or more in diameter, and shaped to the prescribed grade.

To conform to Sediment and Stormwater Management requirements, all disturbed areas shall be seeded and matted within 14 calendar days following exposure.

 **METHOD OF MEASUREMENT -** When paid by surface area measurement, this item shall be measured by the square yard along the surface area actually covered with matting not including overlaps or check slots, with all the work specified above, completed and accepted within the limits of the project.

 When paid lump sum, this item will not be measured; however, the work to be paid for shall be that required to complete the project, performed in accordance with the requirements of these specifications, complete, in place, and accepted.

 **BASIS OF PAYMENT -** The quantity of Seeding & Soil Stabilization Matting, measured as determined above as applicable to this contract, will be paid at the contract unit price bid for this item, which price and payment shall be full compensation for preparation of the grade, furnishing, hauling and placing all materials, and for all labor, equipment, tools and incidentals necessary to complete the work.

**NOTE: Seeding & Soil Stabilization Matting may be paid either by surface area measurement or lump sum. The bidder is instructed to refer to the “PROPOSAL AND SCHEDULE OF PRICES” included in this bid package to determine which method applies to this contract.**

****

**ITEM #SP-39 SUMP PUMP**

**DESCRIPTION OF WORK -** This item shall consist of connecting existing sump pump discharge pipes to new or existing drainage facilities. The item includes furnishing and placing pipe, saddles, bends, tees, wyes, reducers, etc. as may be necessary to extend sump pump discharge pipes and to make satisfactory connections to pipe, drainage inlets, endwalls, etc.

**MATERIALS AND CONSTRUCTION METHODS -** Materials shall be new standard fabricated items compatible with and equivalent or superior to the existing sump pump discharge pipe. Construction methods shall be in accordance with industry standards for installing the types of materials required.

**METHOD OF MEASUREMENT -** The number of Sump Pump Connections to be paid shall be the actual number of Sump Pump Connections made, complete, in place, and accepted.

**BASIS OF PAYMENT -** The number of Sump Pump Connections as determined above shall be paid for at the contract bid price per each which price and payment shall be full compensation for all excavation, furnishing and placing all materials, backfilling, and for all labor, equipment, materials, tools and incidentals required to satisfactorily complete the item.

**ITEM #SP-50 PORTLAND CEMENT CONCRETE SIDEWALK**

**DESCRIPTION OF WORK -** The contractor shall install P.C.C. Sidewalk as shown on the plans. This item shall include sawcutting existing sidewalk, removal and disposal off-site of existing sidewalk, excavation for sidewalk, furnishing and placing graded aggregate base course (GABC) for sidewalk, placing P.C.C. sidewalk, backfilling along installed sidewalk, replacing topsoil over backfilled area, and sealing joints.

**MATERIALS AND CONSTRUCTION METHODS -** The materials and construction methods for this item shall conform to DelDOT's Specifications for Sections 302, 705, and 812.

**METHOD OF MEASUREMENT -** The number of square feet of P.C.C. Sidewalk to be paid for under this section shall be the actual number of square feet of P.C.C. Sidewalk measured from end to end, complete, in place, and accepted. The costs of joints and joint sealer shall be included in the price bid per square foot for this item.

**BASIS OF PAYMENT -** The number of square feet of P.C.C. Sidewalk measured as provided above, shall be paid for at the contract unit price per square foot bid for this item, which price and payment shall be full compensation for sawcutting existing sidewalk; removing and stockpiling existing topsoil; removing and disposing of existing sidewalk off-site; excavation; furnishing, hauling, and installing graded aggregate base course and P.C.C. Sidewalk; backfilling with excavation material; replacing stockpiled topsoil over the backfilled area; finish grading of the area to accommodate sod or seed and mulch; and sealing joints. No separate payment will be made for the items herein listed under this item of work.

**\*\*\* THE FOLLOWING PAGES, "PROPOSAL AND SCHEDULE OF PRICES" AND "BID SECURITY" REQUIREMENTS** **MUST BE FILLED OUT AND RETURNED TO CONSTITUTE SUBMITTING A BID.**

PROJECT NAME: Mashallton-Washington Avenue

NCCD Contract No. 1723-02

Bid Opening: Date: September 3, 2020

 Time: 10:00 a.m.

Location:New Castle Conservation District

 2430 Old County Road, Newark, DE 19702

Location of Proposed Work: Mashallton-Washington Avenue New Castle County, Delaware

Contract Time: 30 Working Days

Liquidated Damages $ 1,030 per Working Day

Bid Security: REQUIRED – 10% of bid amount

Performance & Payment Bond: REQUIRED– 100% of contract amount

Retainage: REQUIRED - 5% of contract payments

|  ITEM | **ESTIMATED QUANTITY** | **UNIT PRICE****(written in words)** | **UNIT PRICE****(figures)** | **EXTENDED AMOUNT** |
| --- | --- | --- | --- | --- |
| 201 | LS | CLEARING AND GRUBBING \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit – Lump Sum |  |  |
| 612A | 92 LF | 15” REINFORCED CONCRETE PIPE \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit – Linear Feet |  |  |
| 612D | 134 LF | 24” REINFORCED CONCRETE PIPE \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit – Linear Feet |  |  |
| 612K | 171 LF | 14” X 23” R. C. ELLIPTICAL PIPE \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit – Linear Feet |  |  |
| 705D | 1 EA | CURB RAMP \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit – Each |  |  |
| 708B | 4 EA | 34” X 24” DRAINAGE INLET \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit – Each |  |  |
| 708C | 2 EA | 48” X 30” DRAINAGE INLET \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit – Each |  |  |
| 708H | 1 EA | 72” X 24” DRAINAGE INLET \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit – Each |  |  |
| 742 | 300 HRS | FLAGGER (Fixed Price Contingency Item) Sixty-Six \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & Zero \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit – Hours | $66.00 |  |

| 743 | LS | TEMPORARY TRAFFIC CONTROL AND DEVICES \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit – Lump Sum |  |  |
| --- | --- | --- | --- | --- |
| SP-3 | 9 EA | TEST HOLES OR TEST PITS FORLOCATING BURIED UTILITIES \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit – Each |  |  |
| SP-4B |  190 LF | CHANNEL EXCAVATION \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit - Linear Feet |  |  |
| SP-11 | 215 SY | HOT MIX PATCHING(REMOVAL AND REPLACEMENT) \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit – Square Yards |  |  |
| SP-14A | 20 LF | PCC CURB- TYPE 1 \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit – Linear Feet |  |  |
| SP-14E | 60 LF | INTEGRAL PCC CURB AND INTEGRAL CURB & GUTTER, TYPE 2 \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit – Linear Feet |  |  |
| SP-15B | 150 TN | RIPRAP-R5 \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit – Tons |  |  |
| SP-19B | LS | SCREENED TOPSOIL \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit – Lump Sum |  |  |
| SP-28 | LS | CONSTRUCTION ENGINEERING \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit - LUMP SUM |  |  |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| SP-29A | LS | SEEDING & SOIL STABILIZATION MATTING \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit - Lump Sum |  |  |
| SP-39 | 5 EA | SUMP PUMP/ROOF DRAIN CONNECTIONS \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit - Each |  |  |
| SP-50 | 100 SF | PCC Sidewalk \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit – Square Feet |  |  |
| 763 | LS | INITIAL EXPENSE \_\_\_\_\_ \_\_\_\_\_\_ \_ Dollars & \_\_\_\_\_\_\_\_\_\_\_ \_ CentsUnit – Lump Sum |  |  |
|  |  | TOTAL BID PRICE | $ |
|  |  |  |  |

The undersigned bidder has carefully examined the site of the proposed work, Standard Specifi­cations, General and Special Provisions, Drawings and Addenda, if any, forming a part of this contract designated as NCCD Contract No. 1723-02, Marshallton-Washington Avenue. Upon notice of award by the New Castle Conservation District, the Bidder agrees to execute a contract within 20 calendar days which shall incorporate said plans and specifi­cations, and further, upon notice to proceed shall, at his own cost and expense, furnish the materials, supplies, machinery, equipment, tools, labor, supervision, insurance, any other accessories and services to complete said work either with his own organization or subcontractors.  The work shall be completed to the satisfaction of the New Castle Conservation District in accordance with the plans, specifications and terms of the contract for the lump sum and/or unit prices for the items on the preceding proposal page(s).

Addendum Number(s)\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ have been considered.

**\*\*\*NOTE - It is the contractor's responsibility to check if any Addendum(s) have been issued and include them in his bid price(s).**

Total Amount of Proposal: $

 (Amount in figures)

 (Amount written in words)

For Individuals and Partnerships:

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

 Witness Contractor SEAL

 Address:

For Corporations:

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

 Witness Name of Corporation & Corporate Seal

 Signature of Officer & Title

 Address:

### BID SECURITY

PRINCIPAL: NAME:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_,

MAILING ADDRESS:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_,

SURETY: NAME:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_,

Incorporated in State of\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_,

Principal and Surety, authorized to do business in the State of Delaware with warrant of attorney to confess judgment, are held bound to New Castle Conservation District, in the amount of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ dollars ($ \_\_\_\_\_\_\_\_\_\_\_\_\_\_) to be paid the District, its attorney, successors or assigns. For this payment to be made we bind ourselves, our, and each of our heirs, executors, administrators, and successors, jointly and severally, finally by this document.

The condition of this document is that the Principal shall, if awarded NCCD Contract No. 1723-02, Marshallton-Washington Avenue, execute in writing an agreement with the District and furnish surety, satisfactory to the District, for performance of contract according to plans and specifications.

The execution shall occur within twenty calendar days after written notification of tentative award of the contract to Principal. If accomplished, this bond shall have no effect, otherwise it shall remain in force.

The Principal and Surety have executed and sealed this document on the \_\_\_\_\_\_\_\_\_ day of \_\_\_\_\_\_\_\_\_\_\_ 2020. The corporate name and corporate seal and representative signature are affixed per authority of each corporate governing body.

For Individuals and Partnerships or Corporations:

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

 Witness Contractor Seal

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

 Witness Name of Corporation & Corporate Seal

 Address:

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

 Witness Surety Company Seal

 Attorney-in-Fact

#### Performance and Payment Bond-Bond No.\_\_\_\_\_\_\_\_

PRINCIPAL NAME: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_,

MAILING ADDRESS:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_,

SURETY NAME: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_,

INCORPORATED IN THE STATE OF: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_,

Principal and Surety, authorized to do business in the State of Delaware, are held bound to the New Castle Conservation District in the amount of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ dollars ($\_\_\_\_\_\_\_\_\_\_\_\_) to be paid the District, its attorney, successors or assigns.  For this payment to be made we bind ourselves, our, and each of our heirs, executors, administrators, and successors, jointly and severally, finally by this document.

The condition of this document is that if the bonded Principal, having contracted with New Castle Conservation District for NCCD Contract No.1723-02, Marshallton-Washington Avenue in the amount of $\_\_\_\_\_\_\_\_\_\_\_\_\_\_, shall faithfully execute and perform all work and furnish all material in accordance with plans, specifications, and items of the contract; shall pay to all and every person supplying labor, equipment or material, all sums of money due for labor, equipment and material for which the Principal is liable; shall indemnify and hold harmless the District from damages and claims and liens by persons doing any of the contract work, this instrument shall then have no effect; otherwise it shall remain in force. The Principal shall obtain any necessary consent of surety for changes in plans, specifications, agreements, contract and quantities.

The Principal and Surety have developed and sealed this instrument on the \_\_\_\_\_\_\_\_\_\_ day of \_\_\_\_\_\_\_\_\_\_\_\_ 2020. The corporate name and corporate seal and representative signature are affixed per authority of each corporate governing body.

For Individuals and Partnerships or Corporations:

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

 Witness Contractor (when applicable) Seal

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

 Witness Name of Corporation & Corporate Seal

 By:

 Signature of Officer & Title Seal

For Surety:

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

 Witness Surety Company Seal

 Attorney-in-Fact